## 📋 Overview
QA TRANSFORMATION ROADMAP — 90 / 180 / 360-Day Execution Playbook
By Pankaj Nakhat ¦ pankajnakhat.com ¦ Customise [bracketed] placeholders before use
TRANSFORMATION PILLARS
# | Transformation Pillar | Focus | Phase 1 | Phase 2 | Phase 3
1 | Test Automation & Infrastructure | SDET capacity, tool standardisation, CI/CD integration | Core framework setup | Scale coverage, parallel exec | Self-healing, AI test gen
2 | Quality Metrics & Visibility | DORA metrics, defect leakage, traceability | Dashboard live, baseline set | SLO dashboard, team-level | Predictive signals, trends
3 | Team Capability | Skills dev, mentoring, community of practice | Train QA leads | CoE, SDET onboarding | Craft sessions, certifications
4 | Process & Governance | Risk-based testing, shift-left, SLOs | Defect triage process | Pre-PR gates, SLO defined | Continuous improvement sprints
5 | Technology & Tools | Test orchestration, data mgmt, observability | Tooling & licences | Test data strategy | AI-assisted tooling
PHASE SUMMARY
Phase | Days | Theme | Key Goal | Primary Output | Success Gate
Phase 1 | 1–90 | Foundation | Baseline, quick wins, core infra | Working framework + dashboard | QA leads aligned, metrics live
Phase 2 | 91–180 | Scale & Standardise | Coverage expansion, shift-left, SLOs | Pre-PR gates on all PRs, CoE active | All teams >95% pre-PR pass rate
Phase 3 | 181–360 | Optimise & Evolve | AI testing, culture, thought leadership | Predictive quality, case study published | DORA elite/high, <1 critical escape/qtr

## 📊 Metrics Tracker
METRICS TRACKER — Baseline vs Phase Targets
Fill in yellow cells (Baseline & Actuals). Targets are pre-set — adjust to your organisation's context.
Metric | Unit | Baseline (T=0) | Target 90d | Actual 90d | Target 180d | Actual 180d | Target 360d | Actual 360d
Test Automation Coverage | % |  | +10% |  | +25% |  | +40%
Defect Escape Rate | defects/1000 runs |  | -20% |  | -40% |  | -60%
Mean Time to Recovery (MTTR) | hours |  | -25% |  | -40% |  | -60%
Test Execution Time | minutes |  | -20% |  | -40% |  | -50%
Manual Test Effort | % of sprint |  | -15% |  | -30% |  | -50%
Flaky Test Count | count |  | -30% |  | -60% |  | <5
CI/CD Pipeline Pass Rate | % |  | 85% |  | 92% |  | 97%
SDET / QA Ratio | 1:X |  | 1:8 |  | 1:5 |  | 1:3
Deployment Frequency | deploys/day
Lead Time for Changes | hours
Change Failure Rate | % |  | <10% |  | <5% |  | <2%
Pre-PR Test Pass Rate | % |  |  |  | 95% |  | 99%
💡 Yellow cells = input your data. Targets are illustrative — calibrate to your baseline before locking in.

## 🔧 Phase 1 — Foundation
PHASE 1: FOUNDATION ¦ Days 1–90
1A — Leadership & Communication
Week | Deliverable | Owner | Status | Notes / Detail
W1–2 | QA Transformation Charter | [Name] | Not Started | Vision, pillars, success metrics, governance model
W2 | Stakeholder Alignment | [Name] | Not Started | Kickoff with engineering leads, product, leadership
W2–4 | Communication Plan | [Name] | Not Started | Newsletter, town halls, Slack channel, doc site
W4 | Town Hall #1 | [Name] | Not Started | Current state, transformation vision, 90-day plan, Q&A
W8 | Progress Update | [Name] | Not Started | Wins, blockers, course corrections
W12 | 90-Day Review | [Name] | Not Started | Metrics, lessons learned, Phase 2 readiness
1B — Metrics & Visibility
Week | Deliverable | Owner | Status | Notes / Detail
W1–4 | QA Dashboard Setup | [Name] | Not Started | DORA, defect, automation, team metrics — weekly update
W4–6 | Test Execution Observability | [Name] | Not Started | Result aggregation, failure trends, flaky test quarantine
W6–8 | Defect Triage Process | [Name] | Not Started | Tag all escapes by coverage, root cause analysis, leakage report
1C — Foundation Automation Framework
Week | Deliverable | Owner | Status | Notes / Detail
W1–2 | Repo & Framework Scaffold | [Name] | Not Started | POM structure, config, CI pipeline template
W2–4 | Coding Standards Doc | [Name] | Not Started | Naming, error handling, flakiness mitigation guide
W4–8 | Critical Journey Automation | [Name] | Not Started | Top [X] user journeys automated and running in CI
W8–10 | CI/CD Integration | [Name] | Not Started | Trigger on PR & merge, result reporting, artifact storage
1D — Quick Wins (Top 5 Opportunities)
Week | Deliverable | Owner | Status | Notes / Detail
W1–4 | [Journey 1] — Low effort | [Name] | Not Started | Coverage +X%, immediate ROI
W2–6 | [Journey 2] — Medium effort | [Name] | Not Started | MTTR reduction
W4–8 | [Journey 3] — High impact | [Name] | Not Started | Defect escape reduction
W6–10 | [Journey 4] | [Name] | Not Started | Sprint capacity freed
W8–12 | [Journey 5] | [Name] | Not Started | Pipeline speed improvement
1E — Tooling & Infrastructure
Week | Deliverable | Owner | Status | Notes / Detail
W1–2 | Tool Audit & Selection | [Name] | Not Started | Evaluate current stack, select target tools
W2–4 | Licence Procurement | [Name] | Not Started | Approvals, vendor POC, budget sign-off
W3–6 | Environment Provisioning | [Name] | Not Started | CI runners, staging mirrors, credential vault
W6–8 | Alerting & Monitoring | [Name] | Not Started | Slack alerts for pipeline failures, 30-day log retention

## ⚙️ Phase 2 — Scale
PHASE 2: SCALE & STANDARDISE ¦ Days 91–180
2A — Scale Automation Coverage
Week | Deliverable | Owner | Status | Notes / Detail
W13–16 | Coverage Expansion Roadmap | [Name] | Not Started | Journey-by-journey breakdown, effort & sequencing
W14–18 | Framework Enhancements | [Name] | Not Started | Parallel exec, result aggregation, flaky quarantine
W16–22 | Test Data Strategy | [Name] | Not Started | TDM automation, PII masking, contract/mock setup
2B — Shift-Left & Pre-PR Automation
Week | Deliverable | Owner | Status | Notes / Detail
W13–16 | Pre-PR Smoke Suite | [Name] | Not Started | 5–10 min critical path, contract/API tests
W15–18 | CI/CD Pipeline Enhancement | [Name] | Not Started | Lint → Unit → Contract → Smoke E2E → Integration gates
W18–22 | Developer Experience | [Name] | Not Started | Local runner guide, IDE plugins, pre-commit hooks
W20–24 | Docs & Training | [Name] | Not Started | How-to run tests, add tests, troubleshoot flakiness
2C — Team Standardisation & CoE
Week | Deliverable | Owner | Status | Notes / Detail
W13–14 | QA Center of Excellence Setup | [Name] | Not Started | Bi-weekly sync, guild meetings, shared library process
W14–16 | Automation Ownership Model | [Name] | Not Started | RACI: Dev → unit/contract, SDET → E2E/infra, CoE → platform
W16–20 | Quality Standards Document | [Name] | Not Started | Code review criteria, naming, flakiness SLO
W18–24 | Mentoring & Skilling Program | [Name] | Not Started | 4-week onboarding, office hours, pair programming
2D — Quality Gates & SLOs
Week | Deliverable | Owner | Status | Notes / Detail
W13–16 | SLO Definition | [Name] | Not Started | Pre-PR 100% pass, regression <X% flakiness, leakage target
W16–20 | SLO Enforcement Mechanisms | [Name] | Not Started | Pipeline gates, weekly SLO reports, escalation path
W18–24 | SLO Tracking Dashboard | [Name] | Not Started | Real-time compliance by team, trend charts, alerts
2E — SDET Hiring & Training
Week | Deliverable | Owner | Status | Notes / Detail
W13–16 | SDET Role Definition | [Name] | Not Started | Responsibilities, skills matrix, career path, comp bands
W14–20 | Hiring Plan Execution | [Name] | Not Started | [X] SDETs targeted — internal promos, external hire, contractors
W16–20 | Onboarding Curriculum | [Name] | Not Started | 4-week plan: setup → deep-dive → first PR → autonomous
W20–24 | Internal Training Program | [Name] | Not Started | Bi-weekly SDET Craft sessions, lunch-and-learns

## 🚀 Phase 3 — Optimise
PHASE 3: OPTIMISE & EVOLVE ¦ Days 181–360
3A — AI-Assisted Testing & Predictive Quality
Week | Deliverable | Owner | Status | Notes / Detail
W26–30 | AI-Powered Test Generation | [Name] | Not Started | LLM prompts for BDD, auto-gen from user stories, risk-based priority
W30–36 | Predictive Quality Signals | [Name] | Not Started | Failure prediction, defect prediction, coverage blind spots
W34–40 | Intelligent Test Triage | [Name] | Not Started | Auto root-cause, flaky detection, owner notification & tracking
3B — Self-Healing Tests & Resilience
Week | Deliverable | Owner | Status | Notes / Detail
W26–32 | Self-Healing Framework | [Name] | Not Started | XPath/selector auto-recovery, retry with backoff, dynamic waits
W30–38 | Test Resilience Library | [Name] | Not Started | Anti-flakiness patterns, observable execution, failure playbooks
3C — Continuous Quality Improvement
Week | Deliverable | Owner | Status | Notes / Detail
Quarterly | Quality Reviews | [Name] | Not Started | Executive dashboard, deep-dive by product, improvement prioritisation
Monthly | Test Optimisation Program | [Name] | Not Started | Debt reduction sprints, flaky remediation, suite trimming
Ongoing | Quality Culture Initiatives | [Name] | Not Started | Test of the Month, open-source contributions, speaking proposals
3D — Thought Leadership & Case Study
Week | Deliverable | Owner | Status | Notes / Detail
W40–44 | Transformation Case Study | [Name] | Not Started | Baseline → results, decisions, ROI, lessons learned
W44–48 | Public Visibility Plan | [Name] | Not Started | LinkedIn article, conference talk proposal, podcast / webinar
W44–52 | Internal Documentation | [Name] | Not Started | QA Playbook, decision log, onboarding curriculum for future leads

## 📅 Weekly Status
QA TRANSFORMATION — WEEKLY STATUS REPORT
REPORTING PERIOD
Week of: | [Date]
Overall Status: | 🟢 On Track / 🟡 At Risk / 🔴 Blocked — delete as applicable
Phase: | Phase 1 / Phase 2 / Phase 3
Prepared by: | [Name]
HIGHLIGHTS (this week)
Win 1: | [Describe win]
Win 2: | [Describe win]
Win 3: | [Describe win]
BLOCKERS & RISKS
Blocker 1: | [Description ¦ Owner ¦ Target resolution date]
Blocker 2: | [Description ¦ Owner ¦ Target resolution date]
Risk: | [Risk description ¦ Severity ¦ Mitigation]
METRICS SNAPSHOT
Automation Coverage: | [X]% → Target [Y]% ¦ Trend: ↑ / → / ↓
Pre-PR Pass Rate: | [X]% ¦ Target 95%
Flaky Test Count: | [X] ¦ Target <[Y]
Defect Leakage: | [X] ¦ Target <[Y]
UPCOMING (next 2 weeks)
Milestone 1: | [Description ¦ Owner ¦ Due date]
Milestone 2: | [Description ¦ Owner ¦ Due date]
Milestone 3: | [Description ¦ Owner ¦ Due date]
DECISIONS MADE
Decision 1: | [Decision ¦ Rationale ¦ Owner ¦ Effective date]

## ⚠️ Risk Register
RISK REGISTER — QA Transformation
Risk | Impact | Probability | Mitigation | Owner | Status | Phase
Tool/licence procurement delays | High | Medium | Early procurement, vendor POC, budget approval | [Name] | Open | 1
SDET hiring challenges | High | Medium | Start hiring early, internal training, contractors | [Name] | Open | 1–2
Flaky test epidemic | High | High | Invest in resilience patterns, team training | [Name] | Open | 1–2
Resistance to change (devs) | Medium | Medium | Early involvement, quick wins, clear benefits | [Name] | Open | 1–3
Test maintenance burden | Medium | Medium | Ownership model, automation-for-automation, tooling | [Name] | Open | 2–3
Scope creep | High | High | Clear prioritisation, exec governance, scope control | [Name] | Open | 1–3
Executive sponsorship loss | High | Low | Regular comms, ROI measurement, visibility | [Name] | Open | 1–3
CI/CD environment instability | Medium | Medium | Dedicated runners, SLA with DevOps team | [Name] | Open | 1–2

## 🐛 Defect Escape Log
DEFECT ESCAPE LOG & ROOT CAUSE ANALYSIS
Defect ID | Severity | Product/Feature | Description | Root Cause Category | Automation Gap? | Action Item | Owner | Status
[DEF-001] | Critical | [Product A / Feature X] | [What broke] | Coverage gap — no test for this scenario | Yes — add test | [Create E2E test for scenario X] | [Name] | Open
[DEF-002] | High | [Product B / Feature Y] | [What broke] | Flaky test — passed intermittently | Yes — fix flaky | [Fix wait strategy in test Y] | [Name] | Open